## Project Tracker
RaceSims Chennai Studio — Payment Tracker
As of 30 June 2026 · 1,146 sq ft Ground Floor · 8 Simulator Rigs
# | Item / Description | Qty | Unit Price | Total (incl. GST) | Paid So Far | Balance | Notes / Rigs
1A · Navkar Computers — PC & Monitor Quote · Ref: Navkar_Quote_Converted.xlsx · 19 Jun 2026
1 | LG XENEON FLEX 45" OLED Monitor (CWBQ65) | 3 | 124999 | 374999 |  | 374999 | SIM-08 (hero rig)
2 | MSI MAG 275F 27" 200Hz Monitor | 3 | 11210 | 33630 |  | 33630 | SIM-01
3 | AMD Ryzen 9 9800X3D Processor | 5 | 47790 | 238950 |  | 238950 | SIM-03/04/05/06/07
4 | AMD Ryzen 7 9700X Processor | 1 | 30975 | 30975 |  | 30975 | SIM-01
5 | Gigabyte B850 Motherboard | 6 | 17464 | 104784 |  | 104784 | SIM-01/03/04/05/06/07
6 | Corsair Nautilus 360 AIO Cooler ★ SPARE | 9 | 8083 | 72747 |  | 72747 | 6 needed + 3 spare sets
7 | Corsair Vengeance 32GB DDR5 RAM ★ SPARE | 9 | 43070 | 387630 |  | 387630 | 6 needed + 3 spare sets
8 | Corsair MP600 Pro 1TB NVMe SSD ★ SPARE | 9 | 17700 | 159300 |  | 159300 | 6 needed + 3 spare sets
9 | NVIDIA RTX 5070 Ti GPU | 3 | 112100 | 336300 |  | 336300 | SIM-04/05/06 (SIM-03 in stock ★)
10 | NVIDIA RTX 5070 TWIN GPU | 1 | 71980 | 71980 |  | 71980 | SIM-01
11 | Corsair RM850e PSU ★ SPARE | 8 | 10325 | 82600 |  | 82600 | 5 builds + 3 spare
12 | Corsair RM1000e PSU | 1 | 17110 | 17110 |  | 17110 | SIM-07 (high-draw rig)
13 | Corsair 3500X Cabinet ★ SPARE | 8 | 8555 | 68440 |  | 68440 | 6 needed + 2 spare
14 | Corsair 4000D Cabinet ★ SPARE | 1 | 8555 | 8555 |  | 8555 | 1 spare unit
1A Subtotal — Navkar |  |  |  | 1988000 | 0 | 1988000
1B · Purchased Separately — Already Paid
15 | Samsung monitors 32" (Odyssey G5 / G6 mix) | 9 | 20750 | 186750 | 186750 | 0 | SIM-03/04/05/06/07 (3× per rig)
16 | NVIDIA RTX 5080 Founders Edition | 1 | 116000 | 116000 | 116000 | 0 | SIM-07
1B Subtotal — Purchased Separately |  |  |  | 302750 | 302750 | 0
2 · Air Conditioning · Subhashree Solutions · Ref: SSS/NEW AC/LEAD NO-0071/26-27 · Rev03 · 25 Jun 2026
17 | LG 4-Way Cassette AC 4.0 TR R32 Single Phase | 2 | 108920 | 217840 |  | 217840 | Main sim floor (open area)
18 | LG Hi-Wall Split 1.5 TR 5-Star R32 Single Phase | 1 | 36222 | 36222 |  | 36222 | Office / training room
19 | AC equipment GST @ 18% |  |  | 45731 |  | 45731 | On equipment subtotal ₹2,54,062
20 | AC installation, materials & commissioning |  |  | 71850 |  | 71850 | Copper pipe, drain, cabling, N2 testing
21 | Installation GST @ 18% |  |  | 12933 |  | 12933 | On install subtotal ₹71,850
AC Total (A+B incl. GST) |  |  |  | 384576 | 0 | 384576
3 · UPS & Batteries · Soundry Power Systems · Ref: SPS/369R1/26-27 · 09 Jun 2026
22 | APC 10KVA Online UPS (SRV10KUXI-IN) | 1 | 113000 | 113000 |  | 113000 | Main power protection
23 | Exide PowerSafe 26Ah SMF Battery 12V | 16 | 2600 | 41600 |  | 41600 | Battery bank
24 | Top Closed Rack + Interlinks + Cables | 1 | 5400 | 5400 |  | 5400 | Incl. delivery + installation
25 | UPS GST @ 18% |  |  | 28800 |  | 28800 | On sub-total ₹1,60,000
UPS Total (incl. 18% GST) |  |  |  | 188800 | 0 | 188800
4 · Electrical, Design & Communications
26 | Designer fee — Sorted Agency | 1 | 50000 | 50000 | 50000 | 0 | Design charges — COMPLETED
27 | Electrical advance — GuruMoorthy / Venus Electricals |  |  | 100000 | 100000 | 0 | Advance for material procurement
28 | Electrical balance + labour (GuruMoorthy) | [5 empty] | Pending final quote
29 | Lighting — LED panels | [5 empty] | Pending quote
30 | TP-Link CCTV / data network / WiFi | [5 empty] | Site visit done — quote pending
4 Subtotal (known paid only) |  |  |  | 150000 | 150000 | 0
5 · Pending Fit-Out (quotes not yet received)
31 | Interior woodwork / joinery | [5 empty] | —
31 | Flooring (tiled carpet) | [5 empty] | —
31 | Painting | [5 empty] | —
31 | Reception desk / counter | [5 empty] | —
31 | Pantry / kitchenette | [5 empty] | —
31 | Doors / locks | [5 empty] | —
31 | Rig platforms / podiums | [5 empty] | —
31 | Fire safety (extinguishers + alarm) | [5 empty] | —
31 | Plumbing | [5 empty] | —
31 | Signage (exterior + interior) | [5 empty] | —
31 | Miscellaneous / contingency | [5 empty] | —
GRAND TOTAL (all quoted lines) |  |  |  | 3014126 | 452750 | 2561376 | + Section 5 pending quotes
★ ₹2,63,199 embedded in Navkar order as spare components (3× cooler/RAM/SSD, 3× PSU, 2× 3500X + 1× 4000D cabinet) — confirm keep or trim