MINDWISE

Work-Backwards Launch Plan

Launch Date: June 1, 2026  •  Planning Date: March 24, 2026  •  69 Days to Launch

# Plan Summary

This plan works backwards from a June 1, 2026 launch date across five parallel workstreams: Brand Identity, Packaging, Website, Marketing/Content, and Team/Operations. Each workstream has dependencies that must be sequenced carefully. The critical path runs through the visual identity presentation (April 2) → website design approval (April 10) → website development (April 11–May 15) → content loading and QA (May 15–28) → launch.

⚠️ CRITICAL PATH BOTTLENECK: The visual identity presentation (due by April 2) unlocks everything downstream—website design, packaging finalisation, social media content, and marketing collateral. Any delay here cascades across all workstreams.

# Phase 1: Foundation & Visual Identity

March 24 – April 2 (Week 1–2)

### Brand Identity

By March 28: Sorted delivers first draft of visual identity / brand book to Mindwise team for pre-review.

By March 28: Manik vets performance/social media agency; confirms availability for April 2 meeting.

By April 1: Sorted delivers one-pager / rough website copy mockup.

By April 1: Sorted delivers updated packaging brief incorporating 11-point feedback (sent March 23).

By April 1: Thambu & Shivendra align internally with partners on website budget range and pricing (₹850–900).

April 2: IN-PERSON MEETING (MUMBAI) — Visual identity presentation, website discussion, meet performance agency, packaging status review.

### Packaging

By March 28: Packaging renders (2 options: premium + realistic backup) delivered by Sorted.

By April 1: Updated packaging brief with corrected dimensions, CDRI logo, blister pack specs, Tic-Tac seal concept.

April 2: Review packaging renders and brief in person. Lock direction.

### Team

By March 28: Manik shares freelance PR contact. Thambu initiates conversation.

By April 2: Meet potential performance/social media freelancer in Mumbai. Assess fit, pricing, scope.

# Phase 2: Lock Decisions & Start Building

April 3 – April 15 (Week 3–4)

### Brand Identity & Design

By April 5: Consolidate feedback from April 2 presentation. Send revision notes to Sorted.

By April 10: Visual identity / brand book LOCKED. Final approved version delivered.

By April 10: Brand guidelines document finalised (colours, typography, logo usage, tone, do’s and don’ts).

### Website

By April 5: DECISION: Proceed with Sorted at ₹6L, negotiate, or engage external developer with Sorted’s brand guidelines. Finalise and sign off.

April 5–10: Website design phase begins (10–15 days from approval). Wireframes and homepage mockup.

By April 10: Website copy first draft from Sorted (or Mindwise team if going external).

By April 15: Website design approved. Handoff to development.

### Packaging

By April 5: Packaging design direction LOCKED (based on April 2 review).

By April 10: Final packaging artwork files sent to manufacturer (Patco Pharmaceuticals).

By April 12: Blister pack design finalised and sent for production.

April 10–15: Manufacturer confirms production timeline; order placed for first batch.

### Team & Marketing

By April 5: Performance/social media agency confirmed and onboarded (or next candidate identified).

By April 7: PR freelancer engaged. Initial briefing on Mindwise story, CDRI-08 angle, founder narrative.

By April 10: Pricing LOCKED at ₹850–900. Bundle pricing structure defined (e.g., buy 2 get 10% off, buy 3 get 15% off).

By April 15: Social media handles set up or refreshed (Instagram, Facebook, LinkedIn, YouTube). Bio, profile images, and brand visuals updated using approved brand identity.

# Phase 3: Build & Create

April 16 – May 7 (Week 5–7)

### Website Development

April 15 – May 15: Shopify development (30–35 days). Homepage, product page, supporting pages built.

By April 25: First development preview (homepage + product page). Team reviews.

By May 1: Razorpay integration, email capture (Klaviyo), analytics (GA + Meta Pixel) configured.

By May 7: All pages complete. Internal QA begins. Mobile responsiveness tested.

### Content & Marketing

By April 20: Brand film brief finalised. Production timeline mapped (if applicable for launch).

By April 25: First batch of social media content created (15–20 posts). Mix of educational, product, and lifestyle content.

By April 30: FAQ page content finalised. Customer testimonials gathered from existing Amazon reviews and early users.

By May 1: Influencer/creator shortlist prepared. Outreach begins for launch partnerships.

May 1–7: Pre-launch teaser content starts going live on social media. Build anticipation.

### Packaging & Product

By April 25: First packaging samples received from manufacturer. Review and approve.

By May 1: Production run started for launch inventory (target: initial batch for first 1–2 months).

By May 7: Product photography completed with final packaging (for website, social media, Amazon listing update).

# Phase 4: Pre-Launch

May 8 – May 25 (Week 8–10)

### Website

May 7–12: Content loading: product images, copy, FAQs, shipping info, reviews loaded into Shopify.

May 12–15: Cross-browser and mobile testing. Performance optimisation (page speed).

May 15–18: Final QA round. Fix any bugs. Test complete purchase flow (Razorpay, email confirmation, shipping).

May 18: Website SOFT LOCK. Only critical fixes after this date.

May 20: Domain configured and pointed. SSL verified.

### Marketing & Social

May 8–15: Pre-launch social media campaign ramps up. Daily posts. Build excitement around the brand story, the science, the “Your Unfair Advantage” positioning.

May 10: PR push begins. Press release drafted and sent. Podcast outreach finalised.

May 12–20: Creator/influencer content goes live (if partnerships confirmed). Seeding to key opinion leaders.

May 15: Email capture landing page live (if website not yet fully live). Start building email list for launch.

May 18–25: Performance ad creatives finalised. Campaign structure built (Meta, Google). Audiences defined.

May 20: Amazon listing updated with new branding, images, A+ content, and revised pricing.

### Operations

By May 15: Packaging production complete. Inventory received and QC’d.

By May 18: Shipping/logistics confirmed (fulfillment partner or self-ship process documented).

By May 20: Customer support process defined (WhatsApp Business, email response templates, return/refund policy).

By May 25: Launch inventory packed and ready to ship.

# Phase 5: Launch Week

May 26 – June 1 (Week 10–11)

May 26–28: Final dress rehearsal. Test end-to-end purchase flow one more time. Verify all links, images, payment. Social media content queued for launch week.

May 29: Website goes live (soft launch). Share with inner circle for final feedback. Monitor for any issues.

May 30: Performance ads go live. Start with small daily budget to test. Monitor CPM, CPC, CTR.

May 31: Final pre-launch social media push. “Launching tomorrow” messaging.

JUNE 1 — LAUNCH DAY: Official launch. Full social media blast. PR coverage goes live. Performance ads scaled. Email blast to subscriber list. Amazon promotions activated. WhatsApp Business ready for customer inquiries.

# Post-Launch: First 30 Days (June 1–30)

Week 1–2: Monitor daily: website traffic, conversion rate, ad performance, social engagement, customer feedback. Optimise ad creatives based on early data.

Week 2–3: Second wave of influencer/creator content. Address any product or shipping issues. Gather and publish new reviews.

Week 3–4: First monthly performance review. Adjust pricing/bundle strategy if needed. Plan July content calendar. Begin planning school-season campaign (June is school start in India).

# Accountability & Due Diligence Checkpoints

To ensure we hold ourselves and all partners accountable, the following review gates are built into the plan:

| Date | Checkpoint | Purpose |
| --- | --- | --- |
| April 2 | Visual Identity Review | Assess Sorted’s brand work. Does it justify ₹6L website? Can we get brand files to explore alternatives? |
| April 10 | Design Lock Gate | All brand assets, packaging artwork, and website design must be approved. No changes after this. |
| April 15 | Development Kickoff Verify | Confirm website development has actually started. Request weekly progress screenshots. |
| May 1 | Mid-Build Review | Website progress check. Packaging sample review. Marketing content first batch review. |
| May 15 | Pre-Launch Readiness | Website feature-complete? Packaging received? Ads ready? If any are NO, assess if June 1 is still viable. |
| May 25 | Go/No-Go Decision | Final launch readiness check. All systems tested. If critical blockers exist, delay to June 15. |
| June 15 | Post-Launch Review | Two-week performance data. What’s working, what’s not. Adjust strategy. |

# Key Risks & Mitigations

Visual identity delayed beyond April 5. Cascades into website, packaging, and content. Mitigation: Agree on hard deadline with Sorted. If missed, escalate to Aarti.

Website budget not approved by partners. Mitigation: Use visual identity presentation + Manik’s one-pager to build the case. Have external developer quotes as Plan B.

Performance agency not a fit. Mitigation: Manik has other contacts. Also explore freelancers on platforms like Pepper Content, Toptal, or through LinkedIn outreach.

Packaging production delays. Mitigation: Order placed by April 15 at latest. Confirm 4–6 week lead time with Patco. Have buffer until May 15.

Scope creep on website. Mitigation: Lock scope at homepage + product page + 5 supporting pages. No new features after April 15 design approval.